## Sheet1
# | Modeling Tasks (Ordered By Priority) | Responsibility | Timeline | Task Type | Comment | Status | Importance | Requiring Funding - Priority Rank
Required Tasks:
1 | On some computers Optipass.exe would not open. Identify the problem and fix it. | Jesse | 2017-02-17 | Fix Model | Anne with work with Jesse to address this issue. Issue: An error message is received which says missing a *.dll file which we believe is one of the files from the C++ redistributable package. This occurred on both home computers and work computers with built in security updates. This was not specific to CDFW computers. The fix that worked for CDFW computers did not work for all computers outside of the Department (i.e., Caltrans). |  | Requirement
2 | Update cost data used by the model so that it is representative of the current costs for all barrier types (diversion dams vs dams). |  |  | Compile Data |  |  | Requirement
3 | Address the NHD looping issue and work with Forum members to make sure appropriate upstream NHDPlus flowline paths are included in the tracing analysis (e.g. lower Calaveras). | Brett | 6-Mar-17 (Calaveras River Sys) and TBD for other watersheds | Compile Data |  |  | Requirement
| Trace barriers along NHD Plus within the watersheds to be tested on March 13, 2017 | Brett, Kate | 2017-03-06 |  | In the output, include all fields provided in the PADForFishPass feature class since they are required by FISHPass.
| Incorporate new tracing and barrier data into FISHPass (Data Portal) and review newly added info/test the model internally | Anne | 2017-03-10
4 | Review/test the model | Small Group - Forum Members | 2017-03-13 | Test Model | Next testing event will be on March 13, 2017. |  | Requirement
5 | Develop a technical plan for creating a fish habitat quality layer to better inform the model. Decide how best to include data available through NHD Plus (i.e., flow) and NorWest (e.g. temperature) into FISHPass. | Forum, S&D Committee, Out-side Biologists/Subject Area Experts, Brett, Jesse |  | Make Decision/ Identify Process | Develop a plan for creating habitat quality, regardless of species. If it proves useful in modifying upstream habitat quantity, later work toward species-specific habitat quality (i.e., establish and use species specific temperature curves). |  | Enhancement
6 | Create a fish habitat quality layer and incorporate NorWest temperature data and data available through NHDPlus (i.e., flows) within the “baseline fish habitat” layer Brett created. | Brett |  | Compile Data | Develop stream habitat quality, regardless of species. If it proves useful in modifying upstream habitat quantity, later work toward species-specific habitat quality (i.e., establish and use species specific temperature curves). |  | Enhancement
7 | Develop a Forum-based request to update the PAD annually. |  |  | Communicate/ Create Documentation | Several barriers included in the model were recently fixed yet this information was not provided to the PAD. Some other barriers are slated for removal, yet they are listed as 'unknown' passage status in the PAD so they were not included in the model. |  | Enhancement, Highly Recommended
8 | Share the new visualization tool with the Forum in March 2017. | Forum | Mar 2017 TBD | Share Model | The data portal (v.1.1.6 and later versions) include map hyperlinks of each barrier suggested for treatment by the model. The next step is to share the revised FISHPass with the Forum.
9 | Supporting Documentation/Appendix Items | Brett, Forum |  | Create Documentation | Document tracing/habitat development and existing model capabilities and constraints to be included as appendix items to the Optipass manual. Include information on the NorWest Temperature model, etc. |  | Requirement
10 | Re-prioritize the longer-term priorities (action items listed below) and secure funding. Discuss with the Forum whether to consolidate the Data Portal and Optipass into one application. This would be a fundamental change and would require major rework. | Stan, Lisa, Forum |  | Make Decision | It might be worthwhile to re-prioritize additional priorities during the September or October Forum meeting. There are 13 longer-term priorities requiring additional funding. Consolidation into one application would be a fundamental change and would require major rework.
Enhancement Tasks:
11 | Remove IP from the model. | Jesse |  | Update Model | IP data is no longer uploaded into the model per decision by the S&D committee; therefore, this should be removed from the Data Portal user-interface. |  | Requirement/ Enhancement | 1
12 | Keep the species sub-weighting as is, but work on the front end with Jesse to make it more intuitive to use. | Jesse, Lisa |  | Update Model | Donnie will contact Jesse within next 2 weeks – solution for review by first week of October 2016 . Has this been implemented? Has Donnie communicated this to Jesse? |  | Enhancement | 2
13 | Enable filtering the analysis input by watersheds or individual “stream systems” outside of the HUC watershed coding system (e.g. entire Klamath basin, or Mission Creek [individual stream system within HUC 12]). | Jesse, Forum Members |  | Update Model | How would this be implemented? It was previously suggested by earlier testing participants and Forum members that Jesse should : "Move HUC 8, 10, 12 to the spatial focus box in Optipass.exe and/or have the hydrography units in Optipass drop down from sub-basin to sub-watershed, and have a search box so that the user may search for keywords in the watershed (i.e., Yuba, Calaveras, and Eel). " (Summary of FishPass model issues, requests and future improvements (2016), Medium Priorities - #13). |  | Enhancement | 3
14 | In post-processing, show the solution (barriers to remove) as text instead of numbers. | Jesse |  | Update Model | Change 0's and 1's to the following per decision at the September 2016 mtg: '0 – DO NOT FIX ' '1 – REMEDIATE IMMEDIATELY' |  |  | 4
15 | It is cumbersome to name Data Portal and Optipass txt outputs based on user options (i.e., OutputFile_AuburnRavineBudget5Mill_WatershedTrtOnly.txt, etc.). Come up with a better solution and implement the solution. | Jesse |  | Update Model or Make Decision? | Keeping track of all of the exports and user-defined inputs from the Data Portal and Optipass could be particularly difficult since there are so many variations available. Possible solutions: Have output txt files from the Data Portal and Optipass "be automatically named by using the inputs specified by the user" and "include an output log to keep track of user’s inputs for each run". |  | Enhancement | 5
16 | Develop and incorporate fish habitat quality into the model using NorWest temperature modeling, etc. in place of IP and remove IP from the model. | Jesse |  | Update Model
17 | Recommend building in individual passability scores for each barrier into the model. Look into the process developed by the North Atlantic Aquatic Connectivity Collaborative to determine passability scores of each barrier. | Anne, Jesse, Forum |  | Update Model or Make Decision? | The model is not reflecting the individual barrier severity or passability of partial/temporal barriers because they are assigned a passability score of 0.5 by default. A user can change the passability scores of individual barriers if they are aware of the severity or passability of the barriers. Some barriers are partially fixed (i.e., retrofit with a fishway, etc.) instead of being fully fixed. A partial barrier which has been retrofitted is still a barrier; however, a less severe barrier. For example, some of the barriers on Mission Creek in Santa Barbara were partially fixed and their passability scores should be 0.7 as opposed to the default setting of 0.5. Should passability be stored in the PAD? |  | Enhancement, Highly Recommended
18 | In the model, include barriers above rim dams and all records where the barrier status is unknown. Where barrier status is unknown, assign a passability score of X (i.e., 0.5) ensuring unknowns are still included in the output. | Jesse |  | Update Model/Compile Data or Make Decision? | During the December 20, 2016 model testing meeting, a couple of barriers within the Alameda Creek watershed were missing from the model because they are listed as unknown passage status in the PAD. These barriers are slated for removal. Currently, the model only analyzes barriers within the current anadromous extent (within Steelhead DPSs boundaries) and not within the historical extent above rim dams. Include barriers within the historical extent to accommodate agencies (e.g., CDOT) which are required to remediate barriers in river systems which historically had anadromous fish and to account for reintroduction programs (Shasta, Yuba, etc.). If we pursue this, PAD would need to obtain barrier information and assessments above dams slated for reintroduction programs, etc. |  | Enhancement
19 | Program FISHPass to recognize watersheds where remediations have occurred. | Jesse, Forum Members |  | Update Model or Make Decision? | It would be good to know where barrier remediations have occurred and continue to fix passage on these streams and systems. Question for testing group: Does this mean that you would like the model to use this information to suggest areas to fix or do you just want to see where this are in the model output, etc? |  | Enhancement
20 | Create a system check to check for any model issues. | Jesse |  | Update Model | System Check: Recommend building in a system check to check for any model issues (i.e., a check to see if barriers from a different watershed/region are included in the analysis of an entirely different watershed/region).
21 | Add gradient data and allow the user to select a gradient/slope threshold (i.e., %2). | Jesse, Forum Members | TBD | Update Model | I believe that Marc envisioned this as a drop down list or as a clickable button in either the Data Portal and/or Optipass. Marc would like to be able to select certain gradient thresholds. Per Jesse, this requires running multiple traces, one for each gradient value.
22 | Include unscreened diversions in FISHPass in the future. For now, include a disclaimer in the model, that diversions are not included in the model and its analysis. | Jesse | TBD | Update Model
23 | Add additional mitigation options to the model (e.g., partial fix, add fishway or modify versus full replacement/removal) | Jesse | TBD | Update Model or Make Decision? | Right now, the model can only work with one mitigation option (i.e., full culvert replacement versus adding fishway at culvert) per the output of the Data Portal.
24 | In the future, include downstream passage in the model as a factor. | Jesse | TBD | Update Model | This would require the PAD to have data that are more comprehensive on downstream passage constraints.
25 | Include other anadromous species in FishPass including sturgeon, pacific lamprey, etc. | Jesse, Forum | TBD | Update Model | This may warrant further discussion with the Forum.
26 | In the future, include different passage statuses/passabilities for each species and lifestages. | Jesse | TBD | Update Model | In order to implement this task, we will need to make the data in PAD more comprehensive. Meanwhile, we should make it clear to the user that in Optipass, the user can only enter 1 in the 'Targets' box.
Ongoing Tasks:
27 | Compile barrier data and updates and provide them to Brett and Kate for tracing along the NHD Plus. | Anne | Annually or As Needed | Compile Data |  |  | Requirement
28 | Trace the barriers along the NHD plus and provide the outputs to Jesse or Anne. | Brett, Kate | Annually or As Needed | Compile Data | The output should include all required fields so it can be fed directly into the model. |  | Requirement
29 | Gather/update cost data for fish passage improvement projects. |  | Annually or As Needed | Compile Data
30 | Add new barrier, tracing and cost data to the model. | Anne, Jesse or Someone Else | Annually or As Needed | Update Model
Completed Tasks:
31 | Fix any existing bugs that affect functionality of FISHPass. | Jesse | 2016-08-15 | Update Model | Done | Completed | Requirement
32 | Provide information to be included in appendices/release notes to Optipass manual to incorporate information about PAD and existing capabilities. | Anne, Outreach and Education Committee | 2016-08-15 | Create Documentation | Provided a one-page summary of the barrier/PAD data used by the model. | Completed | Requirement
33 | Password protect the data portal. | Jesse | 2016-08-15 | Update Model | Done. The password was provided to Anne which was then forwarded to Donnie, Lisa and Stan. | Completed | Enhancement
34 | Forcing out a barrier issue - Anne will send Jesse exact example, and Jesse will ensure it is performing as expected. | Anne and Jesse | 2016-08-15 |  | Done. Sent a map of the Corte Madera run forcing out issue to Jesse and sent another example. It turns out it was an issue with the data that was entered into the model. Working with Jesse, Brett and Kate to ensure that there are no issues with the base data in the near future. May need to exclude data where upstream miles are 0. Rechecked this. There seems to be a misunderstanding of what "forcing-out" a barrier means. It is equivalent to "can't be mitigated" not "has already been mitigated." See previous response in Word doc (dated 11/26/15). | Completed
35 | Jesse will replace the terminology in Optipass from Habitat to Potential Habitat unless he can provide a justification of satisfaction to the Forum. | Jesse | 2016-08-15 | Update Model | Done | Completed | Enhancement
36 | Anne will review priority #4 from the Word document and determine if it has been fixed. Anne should provide Jesse with the exact combination of inputs she used to create the issues. | Jesse, Anne | 2016-08-15 | Check Model | Done, this has now been completed. Before: Waiting for Anne. Believe this was an old coding error that has now been fixed. Need input file Anne used to be sure. Waiting for an updated data portal that can be downloaded. The working document/Summary of Remaining Fish Pass issues noted that this could not be checked since a new debug error occurred. | Completed
37 | Fix manual input to address debug error. | Jesse | 2016-08-15 | Update Model | Done | Completed | Requirement
38 | Some ESU/DPS seem to be default on and others are default off - Anne and Jesse to have a conference call to discuss, develop an approach, and run it by the Forum (recommendation is for DPS to be off unless the user turns them on). | Jesse, Anne, Forum | 2016-08-15 | Check Model | No issue. File wasn't saved with default settings. | N/A. No longer an issue.
39 | Anne will finish adding the red, yellow, green notations to the remainder of the working document, and share with Jesse and Donnie | Jesse, Donnie, Anne | 2016-06-24 | Create Documentation | Waiting for Anne. Done. Completed July 5, due to technical difficulties. | Completed
40 | DRAFT: Provide Jesse with the ownership type for each barrier built into the model. | Anne | 2016-08-29 | Compile Data | Completed on 8/29/2016. Jesse incorporated ownership type into the barrier data in v1.1.9 of the Data Portal. | Completed | Requirement
41 | DRAFT: Decide to 1) keep species sub-weighting as-is or 2) remove the weighting structure and allow the user to manually assign the weights for each target. | Forum, S&D Committee |  | Make Decision | The potential habitat gain is less for a barrier in a coho ESU when you turn on sub-weighting for Coho ESU than if sub-weighting is turned off. Refer to priority #10. The Forum and/or S&D committee should weigh in on this and choose which option makes most sense to them. Question for Donnie, Stan and Lisa: Should we wait until the model is tested by more users (outside of the Forum) before choosing which option we employ? Decision: Keep the species sub-weighting as is, but work on the front end with Jesse/Donnie to make it more intuitive to use. | Completed
42 | DRAFT: Should determine if gravel/borrow pits should be included in the barrier dataset. If this should be included, explain that NA has been assigned under cost since cost for removing these is currently unavailable. There are three of these types of barriers in the PAD currently. Also, investigate the cost used for diversions - is this for screening them or removing them (diversion dams/structures)? Someone will need to look at the cost estimates. Some of these may need be changed to 'dam' site type in the PAD depending on the passage impediment. Anne will look into this. | Forum & S&D Committee (Decisions), Anne (poss. changes to PAD) |  | Make Decision/ Conduct Research | This action item corresponds to Priority #28, we requested “In cost estimates, please consolidate diversions and dams as Dams/Diversion Dams, and explain why Gravel/borrow pits are listed as NA in the “Note to User:”. It is Jesse's understanding is that 'NA' was added to gravel/borrow pits because there is no cost data for these. | Completed
43 | DRAFT: If the Forum would still like to see the solution (barriers to remove) as text instead of numbers on the post-processing page, then the Forum and/or S&D committee needs to decide how they should be displayed. Refer to the Anne and Jesse's comments tied to priority #14. | Forum, S&D Committee |  | Make Decision | Perhaps the S&D committee or Forum has a suggestion for an appropriate term to use (i.e., ‘fix’ or ‘remove’, etc.). If other mitigation options are added at a later data, would Optipass return more than 1 or 0, and would it also return 2 for example (for retrofitting)? The Forum could make a decision now about the different mitigation options for CA and how to assign each (i.e., 1 – remove completely, 2 – install fishway), etc. Currently the FISHPass output shows the result as numbers (0 or 1) instead of text like 1 - remove or 0 - do not remove. Please refer to the priority list. | Completed | Enhancement
44 | DRAFT: Create an updated barrier dataset and provide to Brett Holycross and Kate Sherman. | Anne | 2016-08-18 | Compile Data | Done. Completed on August 18th. | Completed | Requirement
45 | DRAFT: Decide if Oregon barriers downstream and upstream of California barriers should be included in the analysis by FISHPass. | Forum, S&D Committee |  | Make Decision, Implementation, etc. | If this action item is carried forward, additional barriers in OR would need to be incorporated and updated in the barrier dataset, and Jesse would need to add code to the model. Ideally, the code would use the barriers in OR when calculating cumulative passability but would not recommend OR barriers for mitigation unless the Forum decides otherwise. | Completed | Enhancement
46 | DRAFT: Develop fish habitat layer (estimated "fish bearing streams") for the model. This is the '“baseline fish habitat” layer. | Brett, Kate | 2016-12-19 | Compile Data |  | Completed | Enhancement
47 | DRAFT: Trace the barriers within nine priority/testing watersheds and downstream barriers along the NHD plus and provide the outputs to Anne. The output can go directly into the model. | Brett, Kate | 2016-12-20 | Compile Data | Created a trace for the testing/priority watersheds (e.g., Coon, Auburn Ravine, Cross Canal, Calaveras, Pescadero-Butano Creek, Deer Creek, Cow Creek, Alameda Creek, Mission Creek-Frontal Santa Barbara Channel) for the December 20, 2016 model testing meeting. | Completed | Requirement
48 | DRAFT: Review/test the model | Forum, Others | Feb 2017 TBD | Test Model | Tested the model on Dec 20, 2016 within priority/testing watersheds. | Complete | Requirement
49 | Anne to share a previous email with Brett and Van (barrier-specific URL for each barrier from PAD) regarding use of data attributes within PAD and linking to coordinates associated with PAD IDs | Anne, Van, Brett | 2016-06-24 |  | Done, completed on June 17, 2016. | Completed
50 | Create link to individual barrier as well as links to all barriers if there are more in the solution, if doable. Jesse will complete the syntax, leveraging existing applications and data maintenance. | Jesse | 2016-08-15 | Update Model | Done. | Completed
51 | The 12/20/2016 FISHPass testing results included a dam outside of the watershed which are neither upstream or downstream of the selected watershed (Mission Creek in Santa Barbara). | Anne | 2017-02-17 | Fix Underlining Data | Source of Issue: Some of the HUC 12 (sub-watershed) names were incorrect. This was corrected.
52 | Fix model bug/issues identified during the 12/20/2016 FISHPass Testing Mtg. | Jesse | 2017-02-17 | Fix Model | Note: None of these appear to be issues anymore. #2 may have been caused by the HUC 12 field having some incorrect names during data entry that was resolved by Anne. Anne with work with Jesse to address these issues. Model Issues/Bugs Initially Observed: 1) The "Map All" button should link to BIOS and only display the optimal barriers for mitigation instead of all of the barriers in the watershed/system (e.g., Auburn Ravine, Coon Creek and Cross Canal). 2) There is an issue with the 'Region' selection which may be a similar issue which was occurring with the agency type selection. We were unable to select a 'Region' (Central Valley, North Coast, etc.) in the Data Portal. When one region was selected, we received an error message and we were unable to export the data into a text file to be used by the Optimization Model (Optipass.exe). |  | Requirement
Note on F20: Brett Holycross: I think that a text file log with the user-input information would be sufficient to resolve this issue. File names created with all of the user inputs seems to be an awkward way to implement tracking the inputs.