## Project Timeline
Appendix C: FY26 Project Anticipated Timeline
Please input the anticipated relevant timeline for project activities including permitting, design, and implemention.
Type | Estimated Annual Schedule (Month, Year or FY) | Task Milestones | Description
Example: Construction Activities | April 2025 | 95% Design Plans and Specifications | DWR has funds for SJRRP staff operations with an unfunded needs estimated at $1.5 million for construction costs. Requesting a portion of the unfunded needs of the CFPF. See budget narrative/justification.
| June 2025 | Real Estate Actions Completed
| June 2025 | Final Design Plans and Specifications
| August 2026 | Obtain All Permits
| November 2026 | Advertise Project
| January 2026 | Award Construction Contract
| April/May 2026 | Begin Construction
| December 2026 | Complete Construction
Example: Administrative and Environmental Compliance Activities